# CampusGuard Development Plan

Roadmap milestones priorities dependencies and definition of done

| Field | Value |
| --- | --- |
| Project name | CampusGuard AI Powered University Admission Engagement and Information Support System |
| Planning stance | Build one complete vertical slice first, then expand categories |
| Recommended team approach | Module by module with working demo after each milestone |
| MVP deadline goal | A complete explainable prototype before adding advanced AI features |

# 1 Build Strategy

The team should build CampusGuard as a working admission engagement platform before adding advanced research features. The first complete vertical slice should be: approved content -> chatbot answer -> inquiry escalation -> staff response -> admin report. Once that is stable, add document upload, better retrieval, analytics, and multi-college configuration.

# 2 Priority Levels

| Priority | Meaning | Examples |
| --- | --- | --- |
| P0 | Required for MVP demo | Auth, roles, approved content, chat, inquiry workflow, admin dashboard |
| P1 | Important polish and completeness | Document upload, source display, reports, filters, email-style notifications |
| P2 | Advanced or future | Vector search, OCR, multilingual, voice, CRM integrations, predictive conversion |

# 3 Milestone Roadmap

| Milestone | Work | Exit Criteria |
| --- | --- | --- |
| M1 Project setup | Create frontend, backend, database, environment files, README | App runs locally and health API works |
| M2 Database foundation | Create tables for users, roles, institutions, courses, content, inquiries, audit | Migrations run and seed data loads |
| M3 Authentication and RBAC | Login, JWT, role middleware, route protection | Each role lands on correct dashboard |
| M4 Admin content management | CRUD for courses, fees, facilities, FAQs, notices, approval status | Approved content appears in public views |
| M5 Chat and retrieval MVP | Question API, domain detection, approved content search, answer formatting | Common questions return verified answers or clarification |
| M6 Inquiry workflow | Inquiry form, assignment, staff response, status history | User can submit and staff can resolve inquiry |
| M7 Dashboards and reports | Admin metrics, staff queue, top questions, unanswered topics | Reports reflect seed/demo activity |
| M8 Document support | Upload PDFs/DOCX, store metadata, extract text where available | Admin can attach documents to content |
| M9 QA and security | Validation, error handling, unauthorized access tests, edge cases | Critical flows pass test checklist |
| M10 Deployment and viva prep | Docker/cloud setup, demo data, screenshots, final docs, presentation support | Demo can be run repeatably |

# 4 Dependencies

| Task | Depends On |
| --- | --- |
| Chat answer API | Approved content schema and seed data |
| Staff dashboard | Inquiry table and authentication |
| Admin reports | Chat logs and inquiry status history |
| Multi-college support | Institution table and tenant scoping from the start |
| Document upload | Admin auth and content management |
| Advanced AI retrieval | Stable approved content repository |
| Deployment | Environment configuration and database migrations |

# 5 Suggested Folder Structure

Use a structure that separates frontend, backend, database, and documentation clearly.

| Folder | Purpose |
| --- | --- |
| frontend/ | React application, pages, components, API client, styles |
| backend/ | FastAPI application, routes, services, schemas, auth, tests |
| database/ | SQL migrations, seed data, ER diagram |
| docs/ | PRD, SRS, architecture, UI/UX, development plan, viva notes |
| uploads/ | Local development file storage; ignored from git for private files |
| README.md | Setup, run commands, project overview |

# 6 Testing Plan

| Test Area | What to Test |
| --- | --- |
| Unit tests | Validation helpers, role checks, domain classification, content filters |
| API tests | Auth, content CRUD, chat, inquiries, reports |
| Security tests | Unauthorized access, tenant isolation, unpublished content leakage |
| UI tests | Login, chat flow, inquiry form, staff queue, admin content |
| Data tests | Seed data, migrations, required fields, foreign keys |
| Demo tests | End-to-end flow from parent question to staff resolution |

# 7 Definition of Done

Feature has frontend UI, backend API, validation, and database persistence where needed.

Role permissions are enforced server-side.

Empty, loading, error, and success states are handled.

Important user actions are logged in audit or status history.

At least one positive and one negative test case is documented.

The feature is explainable in viva with data flow and database tables.

# 8 MVP Build Order

Start with database design and seed data for one college.

Build login and role dashboards.

Build admin content management for courses, fees, documents, FAQs, facilities, and scholarships.

Build public pages and chatbot retrieval from approved content.

Build inquiry capture and staff response workflow.

Add reports and top unanswered questions.

Add document upload and extraction support.

Add security tests, UI polish, and deployment.

# 9 Features to Avoid Until Core MVP Works

Facial recognition or biometric systems.

Payment gateway integration.

Real admission decision automation.

Full ERP or SIS integration.

Predictive admission conversion scoring.

Voice and multilingual mode before the text workflow is stable.

Too many separate service modules that become shallow CRUD pages.

# 10 Final External Review Note

CampusGuard is a strong final-year project if the team demonstrates a complete, focused product: verified admission information, applicant and parent engagement, staff follow-up, admin-controlled content, multi-college readiness, and clear security boundaries. It becomes weak only if it is presented as a generic chatbot or if the team adds many unfinished modules without a working core.